## Overview
Track B
Focus: gradual data foundations, Python/Pandas, SQL, basic ETL, GCP/BigQuery concepts, RAG, LLM applications, and an introductory agentic workflow.
Plan Duration | 3 Months / 12 Weeks
Primary Outcome | Standalone Data + RAG Assistant
Expected Final Evidence | Clean GitHub repository, README, simple architecture diagram, sample queries, working local MVP demo, and limitations section
Company Input Needed | Training direction + weekly feedback only
Total Estimated Hours | 191
Average Hours / Week | 15.9
Target Starting Level | Beginner to lower-intermediate: basic Python familiarity and only light AI/data exposure

## Weekly Plan
Track B
12-week gradual practical plan for a trainee who is between beginner and lower-intermediate level. The plan prioritizes fundamentals, repetition, small deliverables, and one realistic final MVP.
Week | Theme | Primary Goal | Core Topics | Practical Tasks | Deliverables | Course Integration | Estimated Hours | Status
1 | Foundation refresh + project setup | Refresh the coding basics needed for data work and create a simple standalone project. | Python functions/modules, virtual environments, files, Git/GitHub basics, REST API concept, SQL basics, SQLite, .env concept. | Create a GitHub repo; set up a virtual environment; read/write CSV and JSON; create a small SQLite database; write basic SELECT/WHERE/GROUP BY queries; add a simple /health endpoint. | Running local project + sample SQLite DB + short setup README. | Google Cloud Fundamentals: optional introduction only | 14 | Not Started
2 | Pandas + practical SQL basics | Become comfortable exploring and manipulating small datasets before building pipelines. | Pandas DataFrames, CSV/Excel loading, data types, missing values, filtering, sorting, groupby, simple joins; SQL SELECT, JOIN, GROUP BY. | Work with a clean sample cost dataset; answer 8-10 questions using Pandas and SQL; compare the same result in both approaches. | Notebook/script with basic analysis + SQL practice file. | No heavy cloud course requirement; focus on hands-on basics | 16 | Not Started
3 | Data cleaning and validation | Learn how to turn imperfect raw data into reliable structured data. | Missing values, duplicates, inconsistent types, text normalization, date parsing, simple outlier checks, schema validation, data quality rules. | Clean a deliberately messy cloud-cost CSV/Excel file; create reusable cleaning functions; produce before/after checks and a short data-quality report. | Reusable cleaning script + cleaned dataset + validation summary. | Professional Data Engineer path: optional introductory data-quality content | 16 | Not Started
4 | ETL pipeline basics | Build a small repeatable pipeline instead of one-off notebook code. | ETL/ELT concept, extract-transform-load steps, project structure, functions, logging basics, error handling, batch processing, SQLite/Postgres concepts. | Create a pipeline that reads raw files, cleans and validates them, then loads the result into SQLite; add simple logs and clear failure messages. | Working local ETL pipeline + documented folder structure. | Professional Data Engineer path: selected beginner pipeline modules | 16 | Not Started
5 | GCP + BigQuery fundamentals | Understand the main Google Cloud data services without requiring advanced cloud administration. | Cloud Storage, BigQuery, datasets/tables, IAM and service-account concepts, public datasets, basic query cost awareness. | If a sandbox account is available, query a BigQuery public dataset and upload a small CSV; otherwise reproduce the same exercise locally and document the cloud equivalents. | GCP/BigQuery notes + 5-8 analytical queries or local equivalents. | Google Cloud Fundamentals: selected core modules | 15 | Not Started
6 | Analytics and simple data modeling | Shape cleaned data so it can support reliable analytical questions. | Aggregations, joins, calculated fields, basic fact/dimension thinking, views concept, reusable SQL queries, simple KPIs. | Create monthly/project/service summaries; build a few reusable SQL queries/views; answer practical cost-analysis questions with evidence. | Small analytics layer + reusable SQL query set + example results. | Preparing for Professional Data Engineer Journey: optional checkpoint | 16 | Not Started
7 | RAG foundations + document preparation | Understand the RAG workflow and prepare documents for retrieval. | RAG concept, embeddings concept, chunking, metadata, PDF/text parsing, vector stores concept, top-k retrieval, source grounding. | Prepare a few fake invoices/policies/reports; convert them to text chunks; attach simple metadata such as month, project, service, and document name. | Small RAG-ready document collection with metadata. | Generative AI specialization: selected introductory RAG/GenAI modules | 16 | Not Started
8 | Build a basic RAG assistant | Create a simple document question-answering flow with citations. | Embedding/retrieval workflow, metadata filtering basics, prompt grounding, citations, missing-information handling, simple evaluation questions. | Build one /rag/ask flow using a small local vector store or managed option if available; test 10 predefined questions and record whether the correct source was retrieved. | Working basic RAG endpoint/app + retrieval evaluation notes. | Generative AI specialization: selected RAG practice | 17 | Not Started
9 | LLM application basics + Gemini/Vertex concepts | Add reliable LLM responses on top of the data and RAG work. | Prompt design, structured JSON outputs, system/user messages, tool/function-calling concept, retries, timeouts, basic hallucination control. | Create simple summarization and insight functions over the cleaned dataset and retrieved documents; require a small structured JSON response. | Simple LLM API/function with structured outputs and fallback behavior. | Vertex AI / Gemini practice: introductory modules only | 15 | Not Started
10 | LangChain basics for data and RAG tools | Learn how an LLM can call a few well-defined tools without building a complex agent. | Chains, retrievers, tools, output parsers, tool calling, basic debugging/logging. | Create 2-3 tools such as search_documents, query_cost_table, and summarize_result; connect them in a simple LangChain flow. | Simple LangChain data-aware assistant + readable tool logs. | LangChain docs + GenAI practice | 16 | Not Started
11 | Intro to Agentic AI + simple LangGraph routing | Understand agentic workflows and build one very small stateful router. | Agentic AI concept, graph state, nodes/edges, router logic, RAG route, SQL route, fallback, validation, simple guardrails. | Build a small graph: classify question → choose RAG or SQL → run one tool → validate result → answer. Keep only two main routes and one fallback. | Beginner LangGraph workflow that routes between document and data questions. | Agentic AI on Google Cloud: selected beginner modules | 18 | Not Started
12 | Capstone integration, demo, and documentation | Combine the strongest parts of the training into a clear junior-level final MVP. | Integration, test questions, README, architecture diagram, limitations, basic logging, future improvements. | Integrate ingestion/cleaning + SQL analytics + basic RAG. Add the LangGraph router only if stable. Prepare 8-12 demo questions, document setup, and present the data flow and limitations. | Final GitHub repo + working local Data + RAG Assistant demo + documentation. | Review selected course modules and key concepts | 16 | Not Started

## Course Mapping
Course Integration Map — Beginner-Friendly
Courses support the practical plan; they are not treated as certification-prep requirements. Only selected beginner-friendly modules should be completed when they directly help the weekly tasks.
Course / Path | Usage | Recommended Timing | Why Included | Source URL
Google Cloud Fundamentals: Core Infrastructure | Recommended selected modules | Weeks 1 and 5 | Introduce cloud vocabulary and the GCP services used later without overwhelming the trainee. | https://partner.skills.google/course_templates/60
Professional Data Engineer Certification path | Optional selected beginner modules | Weeks 3-6 | Use only introductory pipeline, BigQuery, reliability, and data-quality modules that match the practical work. | https://www.cloudskillsboost.google/paths/16
Preparing for your Professional Data Engineer Journey | Optional checkpoint | Week 6 | Use as a light self-assessment and domain map, not as exam preparation. | https://www.cloudskillsboost.google/paths/16/course_templates/72
Generative AI Specialization / Skill Badge alignment | Recommended selected modules | Weeks 7-9 | Support RAG and GenAI concepts after the trainee has enough data foundations. | https://partner.cloudskillsboost.google/paths/422
Agentic AI on Google Cloud | Selected beginner modules only | Week 11 | Introduce agentic concepts after RAG, SQL, and basic LLM tool use are already understood. | https://www.cloudskillsboost.google/paths/3273
Professional Machine Learning Engineer Certification path | Optional / not required | Only after Week 9 if extra time exists | Not needed for the core track; use only for extra LLM/ML systems context. | https://www.cloudskillsboost.google/paths/17

## Final Demo
Final Practical Demo — Beginner-Friendly MVP
Local-first prototype: no company repo, no company data, and no production access required.
Item | Description
Project Name | Standalone Data + RAG Assistant
Goal | Build a small local application that cleans a synthetic cost dataset, answers numeric questions with SQL, and answers document questions with RAG.
Allowed Data | Synthetic cloud billing CSV/Excel, deliberately messy sample files, generated invoice/policy PDFs, and public documentation.
Core Features | Data ingestion and cleaning, SQLite/SQL analytics, metadata-rich basic RAG, structured LLM responses, and an optional simple LangGraph router between SQL and RAG.
Expected Demo Questions | Which project had the highest cost? Which service increased the most? What does the sample policy say about a cost rule? Show the SQL result or document source used for the answer.
Final Evidence | Clean GitHub repo, README, simple architecture diagram, sample data, query examples, working local demo, and limitations/future-improvements section.
Success Criteria | The trainee can run the project locally, explain each major step, answer predefined data questions with SQL evidence, answer document questions with grounded sources, and clearly state what the MVP cannot do.